| Recommendation for Approval |  |
| --- | --- |
| Project | 30 St Georges Rd, Preston (30SGRP) |
| Reference | Contractor Variation CV037 – Salto Door Locks to Apartments |
| Prepared By | James Niven |
| Total Cost | $767,994.26 (excl. GST) – CV037 claimed and QS-recommended value |
| Position against Budget | $767,994 against $451,000 held budget for this scope item, requiring -$316,994.26 of contingency spend. Recommended for approval notwithstanding the overrun |
| Purpose / Objective |  |
| This document seeks approval to accept Hacer's Contract Variation, CV037, for the supply, installation and commissioning of a SALTO electronic door locking system to all 473 apartment entries at 30SGRP and associated contingency spend. |  |

| Key Items |  |
| --- | --- |
| Financial Terms |  |
| Cost Code | 17111.05109 – “Spare 1 - Salto Locks” |
| Budget | $451,000 |
| Cost | $767,994.26 |
| Budget Position | -$316,994.26 |
| Budget Transfers | -$316,994.26 from Construction Contingency to Head Contract ($10,811,067 remaining) |
| Revised Budget | $10,811,067 remaining |
| Other Budget Cost Forecast | N/A |
| Comments | -Original $451,000 allowance was benchmarked off 402 Macaulay Road rates. -Hacer's CV037 pricing instead reflects more recent Victoria St, Brunswick (VSB) costs. -Per Slattery's independent assessment (8 Sept 2026): the VSB project equated to approximately $1,381 per door versus $1,476 per door for 30SGRP; -Allowing for the timing gap between the two projects' delivery, Slattery consider the CV037 costs fair and reasonable and have recommended the amount in full. |
| Feasibility Impact |  |
| Project Impact | No extension of time applies. Project to align with SWK & Heathcote portfolio. |
| Budget and Contingency Position | Construction Contingency -$316,994.26 $10,811,067 remaining. |
| 7. Internal Notes and Approvals |  |
| Delegated Authority | - Value (-$316,994.26) < than $1,000,000 – Head of Delivery Sign-off Required - No Owner (HESTA) approval required; standard PCG notification applies. |
| Supporting Documents | -Annexure A – Hacer CV037 Summary & Breakdown, CV037 – Salto Locks to Apartments (6 Aug 2026); -Annexure B – Slattery Variation Recommendation & Assessment Ref 21411-CVCV037 (8 Sept 2026) |

| Name | Position | Signature |  | Date |
| --- | --- | --- | --- | --- |
| Recommendation for Signature |  |  |  |  |
| James Niven | Development Manager |  |  |  |
| Approval |  |  |  |  |
| Sam Delmenico | Head of Delivery |  |  |  |